## Sheet1
FAKE STORE API TEST EXECUTION REPORT
A | B
Project Name | Fake Store API QA Project
Tested By | Muhammad Hassnain Raza
Testing Type | Manual API Testing
Tool Used | Postman
Bug Tracking Tool | Jira
Execution Date | 2026-07-01
Environment | Fake Store API
Test Execution Summary
A | B
Total Test Cases | 10
Executed | 10
Passed | 5
Failed | 5
Blocked | 0
Not Executed | 0
Pass Percentage | 50%
Fail Percentage | 50%
Detailed Test Execution
TC ID | API Endpoint | Method | Expected Result | Actual Result | Status | Bug ID
API_TC_001 | /products | GET | Status 200 | Status 200 | Pass | N/A
API_TC_002 | /products/1 | GET | Status 200 | Status 200 | Pass | N/A
API_TC_003 | /products/999999 | GET | 404 Not Found | 200 OK (Empty Response) | Fail | BUG-001
API_TC_004 | /products | POST | Product Created | Product Created | Pass | N/A
API_TC_005 | /products | POST | Reject Negative Price | Accepted Negative Price | Fail | BUG-002
API_TC_006 | /products/1 | PUT | Product Updated | Product Updated | Pass | N/A
API_TC_007 | /products/1 | PUT | Reject Negative Price | Accepted Negative Price | Fail | BUG-003
API_TC_008 | /products/1 | PUT | Reject Empty Title | Accepted Empty Title | Fail | BUG-004
API_TC_009 | /products/1 | DELETE | Product Deleted | Product Deleted | Pass | N/A
API_TC_010 | /products/999999 | DELETE | 404 Not Found | Success Response Returned | Fail | BUG-005
Defect Summary
Bug ID | Summary | Severity | Priority | Status
BUG-001 | Invalid Product ID returns 200 instead of 404 | Medium | High | To Do
BUG-002 | POST API accepts negative price | High | High | To Do
BUG-003 | PUT API accepts negative price | High | High | To Do
BUG-004 | PUT API accepts empty title | Medium | High | To Do
BUG-005 | DELETE API returns success for invalid product ID | Medium | High | To Do
Test Conclusion
API testing was successfully completed for all CRUD operations using Postman.
A total of 10 test cases were executed.
5 test cases passed successfully.
5 test cases failed due to validation and error-handling defects.
All identified defects were documented and reported in Jira for further investigation and resolution.